## Sheet1
|  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August
| Activity | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4
Admin | Submit Proposal | bar: March Week-2
Research & Planning | Review literature on geometry representation | bar: March Week-3 to March Week-4
Review literature for shape optimisation in low-dimensional space. | bar: March Week-3 to March Week-4
Identify main gaps and establish problem statement.
Define methodology and research approach.
Create MSc thesis report structure.
Write up literature review
Write up metholodogy
Data Collection & Pre-processing | Collect or generate 2D shape dataset.
Pre-process data (resizing, augmentation, normalisation).
Define evaluation metric for low-dimensional representation.
Model Development & Implementation | Create GitHub project structure for model comparison.
Create geometry representation models/methods in Python.
Train & Validate techniques to obtain low-dimensional geometry embeddings.
Assess smoothness, interpretability and effectiveness of representations.
Optimisation Model Integration | Create optimisation technique scripts.
Integrate learned representations into compactness optimisation framework.
Evaluate effectiveness of different representations for optimisation task.