## Sheet1
|  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August
| Activity | Week-1 | Week-1 | Week-2 | Week-3 | Week-4 | Week-5 | Week-6 | Week-7 | Week-8 | Week-9 | Week-10 | Week-11 | Week-12 | Week-13 | Week-14 | Week-15 | Week-16 | Week-17 | Week-18 | Week-19 | Week-20 | Week-21 | Week-22 | Week-23
Admin | Submit Proposal
Ethics approval form
Research & Planning | Review literature on geometry representation
Review literature for shape optimisation in low-dimensional space.
Identify main gaps and establish problem statement.
Milestone: Produced literature matrix.
Create MSc thesis report structure.
Define methodology and research approach.
Write literature review
Write up metholodogy
Milestone: Literature review draft completed.
Data Collection & Pre-processing | Collect or generate 2D shape dataset.
Pre-process data (resizing, augmentation, normalisation).
Define evaluation metric for low-dimensional representation.
Milestone: 2D shape dataset & processed.
Model Development & Implementation | Create GitHub project structure for model comparison.
Create geometry representation models/methods in Python.
Train & Validate techniques to obtain low-dimensional geometry embeddings.
Assess smoothness, interpretability and effectiveness of representations.
Milestone: Geometry Representation techniques tested.
Optimisation Model Integration | Create optimisation technique scripts.
Integrate learned representations into compactness optimisation framework.
Evaluate effectiveness of different representations for optimisation task.
Milestone: Integrated geometry representation and design exploration.
Report Writing & Submission | Draft final dissertation, including results & discussion.
Review & edit final report.
Milestone: Dissertation submitted.